**COVID-19 Outbreak Response Coordination Group for the 9 temporary shelters along the Thai-Myanmar border (Kanchanaburi & Ratchaburi Provinces)**

**15th Meeting, 25 June 2020**

**Participants**: **ADRA** (Udom Raksakunmai, John Smith, Prasit Chairaksaphan), **IRC** (Thidaruch Daewa, Dr. Min Htike), **TBC** (Nakarin Vananeetikul), **UNHCR** (James Ferguson, Yuwarat Thipklai)

**Updates on Previous Action Points:**

|  |  |  |
| --- | --- | --- |
| **Action Point** | **Status** | **Remarks** |
| 1. IOM will follow-up about request for 20 hammocks with mosquito nets for BDY Camp.
 | Completed | UNHCR and IOM collaborated to support BDY Camp Security with 20 hammocks |
| 1. UNHCR will share a copy of rapid protection assessment being conducted in the 9 camps.
 | Completed | Results of 200 completed surveys are being tabulated |
| 1. UNHCR will re-circulate the World Refugee Day proposals from the two camp committees.
 | Completed | WRD activities were held at THI on 19 June, at BDY on 23 June |

**Regular Agenda:**

1. **Situation update**
* No changes for COVID-19, no suspected or confirmed cases in Kanchanaburi or Ratchaburi provinces.
* National level curfew has been cancelled and back-to-school plans at Kanchanaburi and Ratchaburi provinces are underway, planned to start from 1 July with maximum 20 children per classroom. All shops are open and there are new requirements for scan or sign-in at entrances.
1. **Camp Governance**
* ADRA continues to follow-up with camp committees in both camps each week. At THI, an assessment of the Public Address (PA) system is under process. A lockdown continues at both THI and BDY.

**ACTION POINT: 1) ADRA will follow-up internally about the PA system assessment requested at THI.**

1. **Surveillance, Case Investigation and Outbreak Rapid Response**
* Protocols for specimen collection, transportation and testing are underway for BDY.
* For THI, the camp commander does not allow IRC CBA to attend training outside camp with Suan Pheung Hospital due to MOI regulation on camp passes; camp commander suggests hospital staff provide training at the camp on the day that the camp commander is also in the camp, alternatively IRC staff may conduct their own training to CBA after training by hospital staff outside camp.
* A family who re-entered BDY after travel to Myanmar remains under quarantine by camp committee.
1. **Infection Prevention Control (IPC)**
* IPC activities continue as usual at THI and BDY.
1. **Risk Communication & Community Engagement (RCCE)**
* UNUCR updated that Media Monitoring Reports and COVID-19 Dashboards continue to be shared with THI and BDY every 1-2 weeks, and through hand delivery by organizations travelling to the camps.
* TBC printed information from the RCCE message package for camp leaders in both camps and have provided soft files for the computers.
* ADRA updated that a Knowledge, Attitudes and Practices (KAP) survey is planned for THI and BDY later this month, with dates to be confirmed; they survey was conducted at MLA, UMP, NPO, MRM and MLO using tablets, which will be transported to other camps to continue the surveys.
1. **Food assistance**
* TBC updated that six months contingency stock delivery completed to BDY: first delivery included 1300 rice, 310 cooking oil; second delivery planned in August. Six months contingency stock delivery for THI is still in process: already delivered 840 rice, 480 cooking oil, and deliveries to be completed on Friday.
* Previously TBC topped-up the food card system (FCS) consumption value at the same level, and this will be continued through July top-up, including 5% increase; there will be changes in August and details will be communicated later.
1. **Protection + Advocacy – RTG Engagement**
* Information about KRCEE “Safe School Return Guidelines” is still pending. IRC is providing technical support to install handwashing stations at the BDY High No. 1 and POC School in collaboration with SCI. BEST Team plans to re-open school starting from 1 July.
* One previously reported SGBV from BDY continues to be supported by different organizations and is being resolved at the camp level. Medical referral to Sangklaburi Hospital has taken place, with next follow-up scheduled on 30 June.
* Plans for providing Child Protection Referral System (CPRS) and PSEA training to Or Sors at THI and BDY are still pending with COERR and UNHCR.

**ACTION POINT: 2) ADRA will share KRCEE “Safe School Return Guidelines” after the meeting.**

1. **AOB**
* ADRA has created two new positions to support RCCE activities at THI and BDY, an Area Coordinator and Field Officer. ADRA has followed-up with RCCE at national level on language of print materials for use at BDY, which is requested by BDY Camp Commander to be included in Thai language.
* HI will travel to THI and BDY during the week of 6-10 July, including attending THI-CC meeting on 8 July.
* TBC asked about the status of the handwashing station mapping being done by RCCE WG national level.
* UNHCR will chair the 16th meeting on **Monday, 13 July at 10:00 AM**, which will be **combined with PWG**.

**ACTION POINT: 3) ADRA will share email contacts with new RCCE colleagues. 4) ADRA will follow-up on the status of the handwashing station mapping.**