**COVID-19 Outbreak Response Coordination Group for the 9 temporary shelters along the Thai-Myanmar border (Kanchanaburi & Ratchaburi Provinces)**

**6th Meeting, 16 April 2020**

**Participants**: **ADRA** (John Smith), **HI** (Chipo Santidongsakun), **IOM** (Sajith Gunaratine), **IRC** (Thidaruch Daewa, Myo Htet), **TBC** (Nakarin Vananeetikul), **UNHCR** (Yuwarat Thipklai), **SCI** (Thoolei), **RTP** (Phanu)

**Updates on Previous Action Points:**

|  |  |  |
| --- | --- | --- |
| **Action Point** | **Status** | **Remarks** |
| 1. UNHCR to follow-up with camp-based staff at THI & BDY to donate remaining disposable face masks to IRC clinics
 | Done | IRC confirmed of receiving masks in both camps. IRC received 400 masks in THI while BDY will confirm later.  |
| 1. UNHCR will follow-up with Bangkok colleagues about IRC use of VRC at THI & SGBV Committee Office at BDY
 | Pending | James will keep update next week |
| 1. TBC will travel to BDY tomorrow and will update the Camp Leader about suspect case
 | Done |  |
| 1. UNHCR will share translations of “key messages” prepared by RCCE working group
 | Pending |  |
| 1. TBC to share updates on RDR from THI & BDY next week
 | Done | 41 refugees were verified in THI and no one was verified in BDY |
| 1. ADRA to share “Guidance on Home Visits” (Karen & Burmese) with Camp Committees & CBOs involved in case management activities (KWO, SGBV Committee, HSG, KSNG, CIT)
 | Done | ADRA had shared and no feedback of the guideline from camps so far |
| 1. UNHCR will follow-up with SPDO on new procedures for organizations entering Tham Hin
 | Done | UNHCR had shared via email to every organizations  |

**Regular Agenda:**

1. **Situation update**
* IRC had shared COVID-19 had updated on the website of Department of Decease Control (DDC) from MOPH or can get an update from the Provincial’s website. A number of cases from the DDC’s website are different from the Provincial’s website. The information from the Provincial’s website is more accurate. KAN still have 8 cases since 31 March same as in RAT while the case from RAT since 27 March. It’s more than 20 days already that have no more confirmed cases.
1. **Camp Governance**
* The 22 refugees who were in a quarantine room in THI had released. TBC had informed the CC couldn’t handle of situation while ADRA informed these people had released because the time competed. Some people are still coming to camp but not keep in the quarantine room anymore but ask the family and Section Leader to inform people who come back to medical check in the clinic. It’s quite challenge for the CC as someone doesn’t want to report. There were 2 people came to take medicines from BDY clinic and went back to Halochanee in Myanmar side. While the other 2 persons came back and decided to leave camp to stay outside instead of staying for 21 days in quarantine room in BDY. Some people blame to CC on accessing to the camp. UNHCR can talk to the camp commanders if CC needed support
* BDY CC request for 2 batteries for PA system.

**ACTION POINTS: 1) ADRA will follow with CC if they need support for camp commanders then inform UNHCR 2) UNHCR will circulate the request for 2 batteries to all NGOs and provide to BDY CC as soon as possible**

1. **Surveillance, Case Investigation and Outbreak Rapid Response**
* IRC is continuing to work on surveillance and provides knowledge for security team for both camps.
1. **Infection Prevention Control (IPC)**
* IRC does the same as mentioned on the previous meeting.
1. **Risk Communication & Community Engagement (RCCE)**
* ADRA keeps sharing the minute meetings to CC in both camps.
* KWO in SKB is making some masks and plans to provide for both camps. A number of masks are unknown yet.
* IRC will provide ToT training to ADRA staff and ADRA staff will provide to camp staff.
* CC had formed the Covid-19 staff for both camps
* IRC got support from RAT MOPH for fabric and some materials to make some masks to THI CC yesterday which can make around 3,000 pieces of mask.
* THI camp commander informed IRC of the Thai Red Cross Society (TRCS) plan to provide materials for refugees to produce masks and they will pay for labour cost. IRC will get confirmation from the camp commander again. This is a good opportunity for THI refugees and IRC will try to find something like this for BDY too.
* IRC asked if ADRA would do a survey by borrowing some tablets from IRC. ADRA has not hear yet but will be check.

**ACTION POINT: 3) IRC will follow up with THI camp commander on producing of face masks from the TRCS**

1. **Food assistance**
* Food card system working group (FCSWG) in both camps conducted daily infection prevention monitoring to vendors to ensure the infection prevention protocol was strictly followed by all vendors.
* There is no issue for wholesalers. They follow the rules strictly.
* TBC had looked at their transection in the beginning of April and found some rice and oil would not enough for 3 months in THI so they ordered more and will deliver this week.
* 5% top-up on food cards.
* TBC prepares for some kitchen materials in case IRC established the isolation room and will support the 2 cookers in each camp. IRC plans to train these cookers.
1. **Protection + Advocacy – RTG Engagement**
* UNHCR had postponed case at the RAT court. No report on SGBV and related cases. UNHCR regular contacts to the camp commanders.
1. **AOB**
* COERR had delivered some coffee to both camps but BDY CC still makes a request therefore UNHCR will follow up with COERR.
* New 10 black rangers visited to BDY and to clinic wither if the clinic is ready to receive COVID-19 patients. Then they went to visit the KWO and the camp security. They visited is positive.
* IRC will use the SGBV office later. The SGBV staff had got an inform. IRC plans to use VRC in THI
* UNHCR will chair the 7th meeting on **Thursday, 23 April at 1:30 PM.**

**Action point: 4) UNHCR follow up COERR to see a sufficiency of coffee for both camps.**